## Slide 1
GIC Delivery Update
23rd Feb 2018

## Slide 2
AGENDA
01
02
03
04
05
06
07
08
09
10
Optum - UHG
Kotak Bank
Oman Arab Bank
AM Bank
FADV
Quarterly Billing vs Achieved
Resource Productivity
RA Details
POC’s
Resource Tracking

## Slide 3
Project Status – OPTUM (UHG)
OPTUM - UHG |  |  |  |  |  |  |  |  |  | 
PROCESS NAME | CURRENT PHASE | CURRENT PHASE COMPLETION DATE | OVERALL PROJECT COMPLETION (%) | START DATE (PLANNED) | END DATE (PLANNED) | END DATE (ESTIMATED) | VARIANCE |  |  | 
 |  |  |  |  |  |  | RESOURCE |  | SCHEDULE | COST
 |  |  |  |  |  |  | Planned | Actual |  | 
PNSO-GLO | Go-Live | 31-Mar-2018 | 95% | 15-Jul-16 |  | 31-Mar-2018 |  |  |  | 
PNSO- ID Creation | Go-Live | 15-Mar-2018 | 95% | 22-Jul-16 |  | 15-Mar-2018 |  |  |  | 
M&R Claims | Go-Live | 31-Mar-2018 | 95% | 16-Jan-17 |  | 31-Mar-2018 |  |  |  | 
E&I | Go-Live | 31-Mar-2018 | 95% | 16-Jan-17 |  | 31-Mar-2018 |  |  |  | 
Billing | Go-Live | 15-Mar-2018 | 95% | 14-Aug-17 |  | 15-Mar-2018 |  |  |  | 
Chiro/ Rehab | Go-Live | 28-Feb-2018 | 100% | 21-Sep-17 |  | 28-Feb-2018 |  |  |  | 
Summary
  UAT sign off received for M&R, E&I and GLO
  Go live sign off awaited for E&I, M&R, GLO and ID Cards.
  Effort estimations to be submitted for RxCCR
  BRD completed for Prime Plan
  TOPS project to re-initiate
Challenges
  ANOTA demo required
  Closure of support contract
  UiPath resources for CoE

## Slide 4
RPA Project Financials – OPTUM (UHG)
PROCESS NAME | PROJECT COMPLETION % | CURRENT PHASE | CURRENT PHASE COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | MONTHLY BILLING STATUS | 
 |  |  |  |  |  |  |  | Projected (FEB - 18) | Achieved (FEB - 18)
PNSO - CCI | 100% | Completed | Completed | 94,65,600 | 82,49,760 | 12,15,840 | 87% | 9,11,880 | 9,11,880
PNSO - GLO | 95% | Go Live | 31-Mar-18 |  |  |  |  |  | 
PNSO - Author | 100% | Completed | Completed |  |  |  |  |  | 
PNSO-MPQ | 100% | Completed | Completed |  |  |  |  |  | 
ID Creation | 95% | Completed | 15-Mar-18 | 14,96,000 | 11,96,800 | 2,99,200 | 80% | 2,99,200 | 
UMR | 85% | On Hold | Hold | 33,72,030 | 16,86,015 | 16,86,015 | 50% |  | 
M&R Claims | 95% | Go Live | 31-Mar-18 | 29,76,735 | 20,83,715 | 8,93,020 | 70% | 20,83,715 | 11,90,694
E&I | 95% | Go Live | 31-Mar-18 | 18,95,055 | 13,26,539 | 5,68,516 | 70% | 13,26,539 | 7,58,022
M&R UBH | 75% | On Hold | Hold | 38,80,556 | 11,64,167 | 27,16,389 | 30% |  | 
E&I Support | 90% | On Hold | Hold | 61,20,000 | 40,80,000 | 20,40,000 | 67% |  | 
SMS Missing | 70% | On Hold | Hold | 44,47,200 | 31,13,040 | 13,34,160 | 70% |  | 
Billing | 95% | Go Live | 15-Jan-18 | 18,36,000 | 12,85,200 | 5,50,800 | 70% | 5,50,800 | 
Chiro | 100% | Completed | 28-Feb-18 | 10,20,000 | 10,20,000 | 0 | 100% |  | 
TOPs | 30% | Dev | Hold | 35,70,000 | 10,71,000 | 24,99,000 | 30% |  | 
Total |  |  |  | 4,00,79,176 | 2,62,76,236 | 1,38,02,940 |  | 51,72,134 | 28,60,596

## Slide 5
RPA Project Status – KOTAK BANK
Challenges
Data availability is the challenges for all the 4 processes (UPI & IMPS, ATM Recon, ATM, POS Complaints) to complete the development and testing.
CRN Insta Kits – It was put on Hold since the month of Oct, 17. Billing pending for the BRD creation as PO is unavailable.
EEFC & Nostro – This is cancelled by client at Go live stage and billing pending for it.
Salary processing – Multi Robo changes are in UAT.
KOTAK BANK |  |  |  |  |  |  |  |  |  | 
PROCESS NAME | CURRENT PHASE | CURRENT PHASE COMPLETION DATE | OVERALL PROJECT COMPLETION (%) | START DATE (PLANNED) | END DATE (PLANNED) | END DATE (Actual / Estimated) | VARIANCE |  |  | 
 |  |  |  |  |  |  | RESOURCE |  | SCHEDULE | COST
 |  |  |  |  |  |  | Planned | Actual |  | 
UPI & IMPS | Development | 9-Mar-2018 | 62% | 11-Sept-17 | 24-Jan-2018 | 15-Mar-2018 | 10 | 7 | 45 | 
ATM Complaints | Development | 15-Mar-2018 | 53% | 12-Sept-17 | 29-Jan-2018 | 31-Mar-2018 |  |  | 53 | 
ATM Recon | Development | 9-Mar-2018 | 60% | 11-Sept-17 | 11-Nov-2018 | 31-Mar-2018 |  |  | 100 | 
POS Complaints | Development | 15-Mar-2018 | 55% | 11-Sept-17 | 16-Mar-2018 | 31-Mar-2018 |  |  | 11 | 
Salary Processing | UAT | 28-Feb-18 | 80% | 14-Feb-17 | 31-Mar-17 | 28-Feb-18 |  |  | 186 | 
Payment Gateway | Prod support | 6 Feb 19 | Ongoing | 6-Feb18 | 6-Feb-19 | 6-Feb-19 |  |  | 157 | 
EEFC | Cancelled | On 19th Jan 18 | 95% | 21-Feb-17 | 31-Mar-17 | 19-Jan-18 |  |  | 211 | 
Nostro | Cancelled | On 19th Jan 18 | 95% | 21-Feb-17 | 31-Mar-17 | 19-Jan-18 |  |  | 211 | 
CRN Insta Kits | Hold | Hold since Oct 17 | 20% |  |  |  |  |  |  | 

## Slide 6
RPA Project Financials – KOTAK BANK
PROCESS NAME | PROJECT COMPLETION % | CURRENT PHASE | CURRENT PHASE COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | FEB BILLING STATUS | 
 |  |  |  |  |  |  |  | Projected (FEB - 18) | Achieved (FEB - 18)
Payment Gateway | 100% | Completed | 6-Nov-17 | 11,86,800 | 11,86,800 | 0 | 100% |  | 
Salary Processing | 100% | Completed | 15-Dec-17 | 9,68,760 | 9,68,760 | 0 | 100% |  | 
EEFC | 90% | Cancelled | 19-Jan-18 | 11,04,000 | 7,72,800 | 3,31,200 | 70% |  | 
Nostro | 90% | Cancelled | 19-Jan-18 | 8,12,475 | 5,68,733 | 2,43,742 | 70% |  | 
IMPS and UPI Comp. | 60% | Dev | 7-Mar-18 | 7,80,000 | 3,12,000 | 4,68,000 | 40% |  | 
ATM Complaints | 50% | Dev | 12-Mar-18 | 10,40,000 | 4,16,000 | 6,24,000 | 40% |  | 
ATM Recon | 40% | Dev | 23-Mar-18 | PO Awaited |  |  |  |  | 
POS Complaints | 40% | Dev | 16-Mar-18 | PO Awaited |  |  |  |  | 
CRN Insta Kits | 15% | On Hold | 13-Oct-17 |  |  |  |  |  | 
Total |  |  |  | 18,20,000 | 7,28,000 | 10,92,000 |  |  | 
Notes
PO received of Rs 60,493/- for the Phase I change requests (Salary processing & Payment Gateway) and of Rs 21,723/- for Payment Gateway support contract (for 2 moths of this financial year).
PO awaited of Rs 2,73,000/- for Salary processing multi Robo implementation (LIC & PS) & Rs 2,59,200/- for Phase II CRs.

## Slide 7
Project Status – OMAN ARAB BANK
OMAN ARAB BANK |  |  |  |  |  |  |  |  |  | 
PROCESS NAME | CURRENT PHASE | CURRENT PHASE COMPLETION DATE | OVERALL PROJECT COMPLETION (%) | START DATE (PLANNED) | END DATE (PLANNED) | END DATE (ESTIMATED) | VARIANCE |  |  | 
 |  |  |  |  |  |  | RESOURCE |  | SCHEDULE | COST
 |  |  |  |  |  |  | Planned | Actual |  | 
ATM Reconciliation | Go-Live | 28-Feb-2018 | 95% | 15-Nov-17 | 17-Dec-2017 | 28-Feb-2018 | 3 | 4 | 53 | 9,58,274
Outgoing Chargeback | Go-Live | 28-Feb-2018 | 95% | 19-Nov-17 | 25-Dec-2017 | 28-Feb-2018 |  |  | 48 | 
Incoming Chargeback | Go-Live | 28-Feb-2018 | 95% | 21-Nov-17 | 30-Jan-2018 | 28-Feb-2018 |  |  | 23 | 
Summary
BRD sign off received for ATM Recon, Outgoing & Incoming but UAT and Go-live sign off pending.
Outgoing & Incoming Chargeback – The solution is running in live. Application (CBO) url changed causing some issues which highlighted to client. Also developers are fixing any defects raised by client.
Change in requirements – Client has already raised CR of 29 days and still giving requirements around new scenarios.

## Slide 8
Project Financials – OMAN ARAB BANK
PROCESS NAME | PROJECT COMPLETION % | CURRENT PHASE | CURRENT PHASE COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | FEB BILLING STATUS | 
 |  |  |  |  |  |  |  | Projected (FEB - 18) | Achieved (FEB - 18)
ATM Reconciliation | 100% | Go-Live | 8-Feb-18 | 45,60,000 | 18,24,000 | 27,36,000 | 40% | 27,36,000 | 
Outgoing Chargeback | 90% | Go-Live | 8-Feb-18 |  |  |  |  |  | 
Incoming Chargeback | 90% | Go-Live | 8-Feb-18 |  |  |  |  |  | 

## Slide 9
QUALITY REPORT - OMAN ARAB BANK
OMAN ARAB BANK |  |  |  | 
PROCESS NAME | MODULE / ARTIFACT NAME | OWNER | STATUS | ISSUES DESCRIPTION
Outgoing & Incoming Chargeback | Go Live | Ish Tripathi | Open | There is changes in application URL which Is throwing connectivity issues. There are 1 selectors issues which need to be fixed.
Outgoing & Incoming Chargeback | Sol Design Document | Dinesh | Open | Solution Design document still not ready for outgoing & Incoming chargeback

## Slide 10
RPA Project Status – FADV
FADV |  |  |  |  |  |  |  |  |  |  | 
PROCESS NAME | CURRENT PHASE | CURRENT PHASE COMPLETION DATE | OVERALL PROJECT COMPLETION (%) | START DATE (PLANNED) | END DATE (PLANNED) | END DATE (ESTIMATED) | VARIANCE |  |  |  | 
 |  |  |  |  |  |  | RESOURCE |  |  | SCHEDULE | COST
 |  |  |  |  |  |  | Planned |  | Actual |  | 
DQFE | Go Live | 16-Mar-18 | 10% | 4Sept-17 | 16-Mar-18 | 16-Mar-18 |  |  |  |  | 
CSPi | Discovery |  |  |  |  |  |  |  |  |  | 
Summary
  FedEx and Mclane Go live on 8th Feb
  CED and Reddy Ice Go live on 16th Feb
  Generic tabular form Development is completed. Testing in progress in QC environment
  Development of new flows for remaining 49 clients.
Challenges
  Very frequent changes in requirements causing instability of solution.
  Skills gaps of developers burns lots of efforts in review and rework.

## Slide 11
 | FADV |  |  |  | 
PROCESS NAME | MODULE / ARTIFACT NAME | OWNER | STATUS | ISSUES DESCRIPTION | 
DQFE | Go live | Ravi kanth |  | Frequent changes in requirement Few knowledgeable resources | 
FADV Quality Report - WIP

## Slide 12
RPA Project Financials– FADV
PROJECT CODE | PROCESS NAME | PROJECT COMPLETION % | CURRENT PHASE | CURRENT PHASE COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | FEB BILLING STATUS | 
 |  |  |  |  |  |  |  |  | Projected (FEB - 18) | Achieved (FEB - 18)
CCO/0058 | DQF Express | 95% | Go live | 16-Mar-18 | 2,22,00,000 | 1,44,00,000 | 78,00,000 | 65% |  | 

## Slide 13
Project Status – AM BANK
AM BANK |  |  |  |  |  |  |  |  |  | 
PROCESS NAME | CURRENT PHASE | CURRENT PHASE COMPLETION DATE | OVERALL PROJECT COMPLETION (%) | START DATE (PLANNED) | END DATE (PLANNED) | END DATE (ESTIMATED) | VARIANCE |  |  | 
 |  |  |  |  |  |  | RESOURCE |  | SCHEDULE | COST
 |  |  |  |  |  |  | Planned | Actual |  | 
Autopay | Development | 3-Mar-18 | 27% | 23-Jan-18 | 26-Mar-18 | 26-Mar-18 | 2 | 2 |  | 
e-AmBiz Onboarding | BRD Sign off | 23-Feb-17 | 20% | 26-Jan-18 | 9-Apr-18 | 9-Apr-18 |  |  |  | 
IBG Recon | BRD Creation | 23-Feb-17 | 17% | 13-Feb-18 | 23-Apr-18 | 23-Apr-18 |  |  |  | 

## Slide 14
RPA Project Financials– AM BANK
PROCESS NAME | PROJECT COMPLETION % | CURRENT PHASE | CURRENT PHASE COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | FEB BILLING STATUS | 
 |  |  |  |  |  |  |  | Projected (FEB - 18) | Achieved (FEB - 18)
AutoPay | 27% | Development | 3-Mar-18 | 24,90,000 |  |  |  |  | 
e-AmBiz Onboarding | 20% | BRD Sign off | 23-Feb-18 |  |  |  |  |  | 
IBG Recon | 17% | BRD creation | 23-Feb-18 |  |  |  |  |  | 

## Slide 15
Billing Planned & Achievement
MONTH | ACTION | WK1 | WK2 | WK3 | WK4 | WK5 | TOTAL (IN LAKHS)
Jan | Plan | 4,200,000 | 2,421,443 | 1,068,175 | 4,561,116 | 638,500 | 12,889,234
 | Ach. | 200,000 | 1,273,500 | - | - | 7,34,400 | 22,07,900
Feb | Plan | 5,417,800 | 6,448,716 | 2,396,500 | 2,123,200 | 2,373,417 | 18,759,633
 | Ach. | 5,218,000 | 5,411,880 | 1,948,716 | - | - | 12,578,596
Total Planned (In Lakhs) |  |  |  |  |  |  | 31,648,867
Total Achieved (In Lakhs) |  |  |  |  |  |  | 14,786,496

## Slide 16
RESOURCE PRODUCTIVITY (sample data)
ACCOUNT | RESOURCE COUNT | MONTHLY CAPACITY (HRs) | ESTIMATED EFFORTS (HRS) | ACTUAL EFFORTS (HRS) | EFFORT VARIANCE(HRs) | UTILIZATION % | ACTUAL RESOURCE REQUIREMENT
OPTUM - UHG | 11 | 1760 | 1700 | 1640 | 60 | 93% | 10
KOTAK | 10 | 1600 | 1600 | 1740 | -140 | 109% | 11
OMAN |  |  |  |  |  |  | 
FADV | 15 | 2400 | 2000 | 1800 | 200 | 75% | 11
AM BANK |  |  |  |  |  |  | 
TCL |  |  |  |  |  |  | 

## Slide 17
RA Details
PO Status | Account | Location | Billing Start Date | Duration in Months | No. Of Positions | No. Of Profile Shared | No. of Interview(s) Conducted | Candidate Selected By Client | Monthly Rate | Total Deal Value | Request Status | Feb'18 | Mar'18 | Apr'18
Received | Genpact | Hyderabad | 31-Jan-18 | 6 | 1 | 1 | 1 | 1 | $6,160 | $36,960 | Deployed |  | $6,160 | $6,160
Received | Optum | Gurgaon | 12-Feb-18 | 3 | 2 | 2 | 2 | 2 | $4,400 | $26,400 | Deployed | $13,200 |  | 
Received | Scope | Chennai | 1-Jan-18 | 6 | 12 | 0 | 0 | 12 | $3,333 | $240,000 | Deployed |  | $60,000 | $60,000
 | Total |  |  |  | 15 | 3 | 3 | 15 | $13,893 | $303,360 |  | $13,200 | $66,160 | $66,160

## Slide 18
POC’s
PO Status | Account | Location | Billing Start Date | Duration in Months | No. Of Positions | No. Of Profile Shared | No. of Interview(s) Conducted | Candidate Selected By Client | Monthly Rate | Total Deal Value | Request Status
 | Cebuana Lhuiller | Philippines | 28-Jan-18 |  | 2 | 2 | 0 | 2 |  |  | Closed
 | Daimler | Pune |  |  | 1 | 1 | 0 | 1 |  |  | Completed
 | MayBank | Gurgaon | 30-Jan-18 |  | 2 |  |  |  |  |  | Completed
 | Merck | Bangalore |  |  | 2 | 1 | 0 | 1 |  |  | Completed
 | One India | Gurgaon |  |  | 2 | 2 | 0 | 2 |  |  | Completed

## Slide 19
Resource tracking

## Slide 20
Handover Session from Sales to Delivery
Actionable | Owner | Duration
Account overview. Why is the project important to the client? What is the significance of the project milestones and/or due dates? Who are the key players? The contracted engagement and commercial terms. Who are the key players? Client expectations | Sales | 60 Min
Hand over of project initiation documentation | Pre-Sales | 60 Min
Details of client development environment (technical or practical dependencies, Architecture ) | Pre-Sales | 120 Min
Solution Design walk through | Pre-Sales | 120 Min
Code handover (in case of existing POC’s) | Pre-Sales | 240 Min
Discussion on project Estimates, High level project plans | Pre-Sales | 60 Min
SOW walk though | Pre-Sales | 30 Min
Formal introduction of Delivery team with Customer | Sales | 30 min

## Slide 21
Required Attendees
Account Manager
Team Leads
Project Manager’s/ Technical Manager
Solution Architect (Delivery)
BA

## Slide 22: Thank You