## Slide 1
GIC Delivery Update
6th JAN 2017

## Slide 2
RPA Project Status / Dashboard
EMS External Project Status / Dashboard
Billing Plan & Achievement
Agenda

## Slide 3
Project Status – On target, with minimum delays
Awaited Go live signoff for CCI, UHCG, Author & SBC.
MPQ development pushed further to 23rd Jan due to SME unavailability.
GLO - During UAT, Issues identified got fixed by 30th Dec, yet to be verified by the SME. Template changed, requires the effort to be part of the CR process.
ID Creation – Received a go ahead to start the testing after 4 months on Hold.
Rx-CCR - Awaiting payment confirmation / signoff.
Billing Status – 70% Closure, 30% moved to Jan
Target billing for Dec-16 delayed – INR 35.43 Lacs, Expected closure – INR 25.37
Jan-17 – INR 76.68 Lacs – On Target, with minimum change due to delay in MPQ
Challenges / Delays / Action Items – To be discussed with UHG team (6th Jan 17)
CCI, UHCG, Author & SBC – Go live signoff is pending for more then a week.
GLO – Template changed, which required additional development ( 20 days + UAT/Sign-off). CR process need to be raised.
RPA Project Status – OPTUM-UHG

## Slide 4
RPA Project Status – OPTUM-UHG
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | PENDING BILLING | REVENUE ACHIEVED (%) | BILLING STATUS | 
 |  |  |  |  |  |  | DEC | JAN
PNSO - CCI | 95% | 30-Dec-16 | 94,65,600 | 28,39,680 | 66,25,920 | 30% | 19,56,360 | 4,669,560
PNSO - GLO | 80% | TBD |  |  |  |  |  | 
PNSO - Author | 100% | 30-Dec-16 |  |  |  |  |  | 
PNSO-MPQ | 33% | TBD |  |  |  |  |  | 
ID Creation | 95% | 15-JAN-17 | 14,96,000 | 11,96,800 | 2,99,200 | 80% | 0 | 0
UHCG | 95% | 30-Dec-16 | 33,86,400 | 16,93,200 | 16,93,200 | 50% | 0 | 1,693,200
SBC | 100% | 30-Dec-16 | 25,16,000 | 15,09,600 | 10,06,400 | 60% | 10,06,400 | 10,06,400
Rx-CCR | 80% | On Hold/Closed | 19,35,630 | 5,80,689 | 5,80,689 | 30% | 5,80,689 | 0
UMR | 20% | 10-FEB-17 | 33,72,030 | 10,11,609 | 23,60,421 | 30% |  | 
Total |  |  | 2,21,71,660 | 88,31,578 | 1,25,65,830 |  | 25,37,049 | 76,68,360
PROCESS NAME | BUDGETED EFFORT (MAN DAYS) | ACTUAL EFFORT (MAN DAYS) | % RESOURCE UTILIZATION | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT MARGIN (PLANNED) | PROJECT MARGIN (ACTUAL) | PROJECT MARGIN (PLANNED) % | PROJECT MARGIN (ACTUAL) %
PNSO – CCI | 120 | 660 | 144% | 10,000 | 6,670 | 71,55,600 | 62,68,730 | 76% | 65%
PNSO – GLO | 151 |  |  |  |  |  |  |  | 
PNSO – Author | 165 |  |  |  |  |  |  |  | 
PNSO-MPQ | 24 |  |  |  |  |  |  |  | 
ID Creation | 60 | 87 | 145% | 5,000 | 0 | 11,91,000 | 10,60,350 | 80% | 71%
UHCG | 109 | 199 | 183% | 0 | 0 | 28,41,400 | 24,72,400 | 84% | 71%
SBC | 108 | 260 | 241% | 5,000 | 4,128 | 19,71,000 | 12,15,172 | 78% | 48%
Rx-CCR | 82 | 102 | 124% | 10,000 | 104 | 15,15,630 | 14,25,526 | 78% | 74%
UMR | 131 | 45 | 34% | 20,000 | 2,25,650 | 26,97,030 | 31,46,380 | 80% | 93%
Total | 950 | 1354 |  | 50,000 | 16,494 | 1,73,71,660 | 1,53, 84,466 |  | 

## Slide 5
RPA Project Status – SCOPE INTERNATIONAL
PROCESS NAME | BUDGETED EFFORT | ACTUAL EFFORT BURNT | % RESOURCE UTILIZATION | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT MARGIN (PLANNED) | PROJECT MARGIN (ACTUAL) | PROJECT MARGIN (PLANNED) % | PROJECT MARGIN (ACTUAL) %
Com-ACC Maintenance | 144 | 60 | 42% | 12,72,100 | 61,808 | 33,14,900 | 56,03,754 | 52% | 88%
Com-Off Boarding | 216 | 74 | 34% |  |  |  |  |  | 
 |  |  |  |  | 50,638 |  |  |  | 
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | PENDING BILLING | REVENUE ACHIEVED (%)
Com-ACC Maint | 40% | 1-Feb-17 | 63,87,000 | 0 | 63,87,000 | 0%
Com-Off Boarding | 45% | 8-Feb-17 |  | 0 |  | 0%
COM Processes (A/C Maintenance & Off Boarding)
Project Updates - BRD Sign off awaited.
Billing Status - PO is pending, escalated, expecting it early next week
Challenges / Delays – Development is delayed on Non-FM A/C Maintenance because of Application access and User availability. Maximizing our efforts to be on target.

## Slide 6
RPA Project Status – SCOPE AUGMENTATION
PROJECT STATUS |  |  |  | 
RESOURCE NAME | PROJECT ASSIGNMENT | START DATE | END DATE | COMMENTS
Dimple Julyani | LMS | 21-Dec-16 | 21-Mar-17 | Development on1st release started
Manoj Singh | GSSC-SCI-II | 28-Nov-16 | 23-Jan-17 | Development on target
Mahesh Babu | RBI-PR | 17-Nov-16 | 23-Dec-16 | Development completed on target date and UAT is in progress. Team started with next release.
Subhrajit Sahoo |  |  |  | 
Prince Makhija | HRSSC- EHF | 16-Nov-16 | 23-Dec-16 | Development completed and UAT is in progress
Rahul Sharma | GSSCI-CSG – BCA | 28-Nov-16 | 16-Jan-17 | Development on but few requirement changed
Sahil Bhandari | Support Devices-ARC | 8-Dec-16 | 6-Feb-17 | Development on1st release started
Yuvraju Madiraju |  |  |  | 
Nitesh Raj | LMS | 21-Dec-16 | 21-Mar-17 | Development on1st release started
Ansuya Kala | Cash Charges | 21-Dec-16 | 15-Jan-17 | Development on target for 2nd release
Sarbeswar | YTD | YTD | YTD | YTD
M. Rafi | LMS | 21-Dec-16 | 21-Mar-17 | Development on1st release started
Project Updates – Out of 7 processes, development completed for 2 (PR & EHF) and rest are on-going as per plan.
Billing status - PO is pending, escalated, expecting it early next week
Additional Q4 requirement – Client is yet to confirm on additional resource requirement, 5 / every month, resources available in pool
Challenges / Delays - Resource replacement identified, hiring plan initiated. Client is not willing to replace, to be discussed. The total resource replacement required is 4 by End Jan/early Feb out of 12 resources. Required Management help

## Slide 7
RPA Project Status – ICICI BANK
Project Updates – Complete sign-off/Email Confirmation by 11-Jan-17.
Billing Status –Client in-principal confirmation awaited (target 6 Jan) to submit the invoice while the email sign-off is in progress
Resources – Moved 1 resource to Mumbai. Hyderabad resource will continue to support (PS Support contract awaited)
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | BILLING STATUS
 |  |  |  |  |  |  | JAN (1st Week)
ATM Dispute I | 100% | Complete | 72,07,200 | 18,01,800 | 44,84,945 (incl. revision on CMS MS) | 25% | 44,84,945
Charge Reversal | 100% | Complete |  |  |  |  | 
Charge Back | 100% | Complete |  |  |  |  | 
ECS Debit | 100% | Complete |  |  |  |  | 
Fund Authorization | 95% | 23-Dec-16 |  |  |  |  | 
FCRM Loan | 95% | 23-Dec-16 |  |  |  |  | 
CMS Master Setup | 40% | Closed | 26,79,227 | 6,69,807 | 20,09,420 | 25% | 20,09,420
CORP-Cust ID | 100% | Complete |  |  |  |  | 
Reversal of Charges | 95% | 23-Dec-16 |  |  |  |  | 
Management Console | 85% | 30-Dec-16 |  |  |  |  | 
Product Billing | 100% | 2-Jan-17 | 1,08,10,800 | 86,48,60 | 21,62,160 | 80% | 21,62,160
Total |  |  |  |  |  |  | 86,56,526

## Slide 8
RPA Project Status – ICICI BANK
PROCESS NAME | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT OVERALL MARGIN (PLANNED) | PROJECT OVERALL MARGIN (ACTUAL) | PROJECT OVERALL MARGIN (PLANNED) % | PROJECT OVERALL MARGIN (ACTUAL) %
ATM Dispute I | 3,27,500 | 7,99,644 | 22,39,700 | -1,906,194 | 31% | -26%
Charge Reversal |  |  |  |  |  | 
Charge Back |  |  |  |  |  | 
ECS Debit |  |  |  |  |  | 
Fund Authorization |  |  |  |  |  | 
FCRM Loan |  |  |  |  |  | 
CMS Master Setup |  |  |  |  |  | 
CORP-Cust ID |  |  |  |  |  | 
Reversal of Charges |  |  |  |  |  | 
Management Console |  |  |  |  |  | 
ATM Dispute II |  |  |  |  |  | 

## Slide 9
RPA Project Status – CELCOM NETWORKS
Celcom Support
Workflow Issue raised by BU, Team is testing and making all the required changes.
Billing Status – Pending submission of the report as per the format suggested. Target to submit by 9-Jan.
Challenges/Delays –
  CPU utilization of NPS robot too high, Live RSIM API Awaited from TCS team.
  Requirements still not finalized and available to us which would impact the development completion date.
CBS Migration Project Update
Pending additional justification requested by TCS and Huawei seeking clarification on the efforts
  Post the meeting on 5th Jan 17, revised efforts with justification to be submitted by 6-Jan
Challenges/Delays –
  Finalized SIT Screens not available to development team, expecting delays from Client (TCS & Huawei)
  Impact assessment not finalized, as per earlier plan the development was supposed to start on SIT 7, moved to SIT 5 and then to Production, new change is exclude SIT 5 from development considering delays on go live and efforts.
  Rework on impact assessment document, to be shared by 6-Jan and expecting sign-off
  Due to change, the go-live is expected around 12-Feb, the same will be communicated today along with revised efforts

## Slide 10
Project Status - DCN
Project Updates - SA integration with share point is in progress. SA integration with cisco wave and cisco prime pending. Secops configuration is in progress by RSA.
Anuranjan Kumar and Mudit Singh are working with RSA PS for configuration of SecOps
Billing Status – Project will be closed by Jan-17 due technical delays
Delay/ Challenges - Parser creation stuck due to inconsistent delimiter in logs, escalated to RSA (Support & Channel Mgr) to look in this issue.
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | REVENUE ACHIEVED (%) | BILLING STATUS – JAN
DCN | 82% | 31-Dec-16 31-Jan-17 | 72,00,000 | 43,20,000 | 60% | 28,80,000
PROCESS NAME | BUDGETED EFFORT | ACTUAL EFFORT BURNT | % RESOURCE UTILIZATION | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT MARGIN (PLANNED) | PROJECT MARGIN (ACTUAL) | PROJECT MARGIN (PLANNED) % | PROJECT MARGIN (ACTUAL) % | OVERALL PROJECT STATUS
DCN | 198 | 62 | 31% | 12,524 | 62,022 | 59,99,476 | 67,66,458 | 83% | 94% | WIP

## Slide 11
Project Status - IFB
Project Update - Munnar call center trial run is in progress and requested EY for UAT and sign off.
Billing Status – Project will be closed by Jan-17
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | REVENUE ACHIEVED (%) | BILLING STATUS – JAN
IFB | 71% | 30-Jan-17 | 37,58,000 | 17,50,500 | 47% | 20,07,500
PROCESS NAME | BUDGETED EFFORT (MAN DAYS) with CR | ACTUAL EFFORT BURNT (MAN DAYS)-OVERALL | % RESOURCE UTILIZATION | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT OVERALL MARGIN (PLANNED) | PROJECT OVERALL MARGIN (ACTUAL) | PROJECT OVERALL MARGIN (PLANNED) % | PROJECT OVERALL MARGIN (ACTUAL) % | OVERALL PROJECT STATUS
IFB | 65 | 48 | 74% | 21,750 | 1,73,642 | 33,46,250 | 32,95,878 | 89% | 88% | WIP

## Slide 12
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | REVENUE ACHIEVED (%) | BUDGETED EFFORT (MAN DAYS) with CR | ACTUAL EFFORT BURNT (MAN DAYS)-OVERALL | % RESOURCE UTILIZATION
HCLi | 33% | 21-Feb-17 | 15,00,000 | 0 | 0% | 180 | 72 | 40%
PROCESS NAME | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT OVERALL MARGIN (PLANNED) | PROJECT OVERALL MARGIN (ACTUAL) | PROJECT OVERALL MARGIN (PLANNED) % | PROJECT OVERALL MARGIN (ACTUAL) % | OVERALL PROJECT STATUS
HCL--APDRP | 10,000 | 14,420 | 4,10,000 | 10,55,020 | 27% | 70% | WIP
Project Update - 2 CA IM resource working on this project
Challenges/Delays – Escalation received due to unavailability of a resource for 20 days, working to mitigate the risk
Billing Status - T&M based project and expected to be closed by 21-Feb-17
Project Status – HCLi-APDRP

## Slide 13
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | REVENUE ACHIEVED (%) | BILLING STATUS-JAN
Verinon-SEBI | 35% | 6-Jan-17 TBD | 3,65,000 | 0 | 0% | 3,65,000
PROCESS NAME | BUDGETED EFFORT (MAN DAYS) with CR | ACTUAL EFFORT BURNT (MAN DAYS)-OVERALL | % RESOURCE UTILIZATION | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT OVERALL MARGIN (PLANNED) | PROJECT OVERALL MARGIN (ACTUAL) | PROJECT OVERALL MARGIN (PLANNED) % | PROJECT OVERALL MARGIN (ACTUAL) % | OVERALL PROJECT STATUS
2FA Implementation | 14 | 14 | 100% | 10,000 | 2,931 | 2,71,000 | 2,78,069 | 74% | 76% | WIP
Project Update - Project is on track.
Challenges/Delays – Customer not available, 1 week of development pending post customer availability.
Billing Status – Project will be completed and billing will be done by Jan-17
Project Status – VERINON-SEBI

## Slide 14
PROCESS NAME | PROJECT COMPLETION % | COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | REVENUE ACHIEVED (%) | BUDGETED EFFORT (MAN DAYS) with CR | ACTUAL EFFORT BURNT (MAN DAYS)-OVERALL | % RESOURCE UTILIZATION
Solusi Technologies | 13% | 31-Dec-16 | 39,73,266 | 6,06,375 | 15% | 106 | 32 | 30%
PROCESS NAME | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT OVERALL MARGIN (PLANNED) | PROJECT OVERALL MARGIN (ACTUAL) | PROJECT OVERALL MARGIN (PLANNED) % | PROJECT OVERALL MARGIN (ACTUAL) % | OVERALL PROJECT STATUS
Solusi Technologies | 6,57,870 | 1,75,524 | 26,79,396 | 36,07,542 | 67% | 91% | WIP
Project Update – On Demand Basis
Billing Status – As per the work done
Project Status – Solusi Technologies

## Slide 15
RESOURCE WISE UTILIZATION (FROM 30 DEC 2016 TO 05 JAN 2016) |  |  | 
RESOURCE NAME | TOTAL AVAILABLE HOURS | BILLABLE UTILIZATION | PRODUCTIVE UTILIZATION
Anuj Choudhary | 700 | 34.18% | 31.21%
Anuranjan Kumar | 700 | 0.44% | 18.75%
Balram Singh Deswal | 660 | 9.5% | 57.86%
Kamal Manchanda | 700 | 59.17% | 32.06%
Ketan Kharbanda | 700 | 16.59% | 31.33%
Mayur Malhotra | 700 | 7.30% | 45.80%
Mudit Singh | 700 | 14.47% | 34.28%
Nabeel Asif | 700 | 13.33% | 40.98%
Pradeep Kumar Pandey | 700 | 9.32% | 51.82%
Sumeet Hooda | 700 | 15.27% | 34.92%
Vinay Chaudhary | 700 | 12.58% | 43.90%
Winkle Khurana | 700 | 25.61% | 26.97%
Hridyesh Srivastava | 700 | 56.97% | 11.21%
Kushagra Sharma | 700 | 51.52% | 9.43%
Saba Iqbal | 700 | 15.00% | 29.24%
Total | 10460 | 25.19% | 35.56%
EMS and Info Sec Team Utilization

## Slide 16
Billing Plan & Achievement
MONTH | ACTION | WK1 | WK2 | WK3 | WK4 | WK5 | TOTAL (IN LAKHS)
Oct. | Plan | 7.9 | 36.0 | 12.2 | 53.3 |  | 109.4
 | Ach. | 24.0 | 6.9 | 16.9 | 0.0 |  | 47.7
Nov. | Plan | 20.7 | 29.6 | 41.4 | 60.0 |  | 151.7
 | Ach. | 3.135 | 22.85 | 7.548 | 4 |  | 37.5
Dec. | Plan | 0.0 | 0.0 | 35.1 | 11.3 | 18.5 | 64.9
 | Ach. | 0 | 0 | 0 | 0 | 0 | 0.0
Total Planned (Q3) |  |  |  |  |  |  | 326.0
Total Achieved (Q3) |  |  |  |  |  |  | 85.3
To be Achieved – Dec’16 |  |  |  |  |  |  | 25.37
To be Achieved – Jan’17 (pending Q3) |  |  |  |  |  |  | 215.77
Above billing doesn’t include ~90Lacs for Scope RA, COM & UHG-UMR project advance

## Slide 17: Thank You