## Current POC's n Projects
| RPA | 6000
Projects | Others | 5000 |  |  |  |  | REVENUE |  |  |  | ACTUAL - OVERALL EFFORT | [5 empty] | REVISED EFFORT |  |  |  | SALARY |  | OVERHEADS |  | MARGIN % |  |  |  | PER DAY MARGIN
OWNER | CLIENT | PROJECT CODE | PROCESS NAME | PROJECT COMPLETION % | CURRENT PHASE | CURRENT PHASE COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | START DATE (PLanned) | PROJECT END DATE (Planned) | BUDGETED EFFORT (MAN DAYS) with CR | BUDGETED EFFORT (MAN DAYS) without CR | ACTUAL EFFORT BURNT (MAN DAYS)-OVERALL | % RESOURCE UTILIZATION | REVISED START DATE (PLANNED) | REVISED EFFORT + CR (MAN DAYS) | ACTUAL EFFORT BURNT (MAN DAYS) | % RESOURCE UTILIZATION | BUDGETED SALARY EXPENSE (ACTUAL PLANNED EFFORT*PER MAN DAY RATE) | ACTUAL SALARY COST (ACTUAL EFFORT*PER MAN DAY RATE) | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT OVERALL MARGIN (PLANNED) | PROJECT OVERALL MARGIN (ACTUAL) | PROJECT OVERALL MARGIN (PLANNED) % | PROJECT OVERALL MARGIN (ACTUAL) % | PLANNED PER DAY MARGIN (INR) | PLANNED PER DAY MARGIN (USD) | ACTUAL PER DAY MARGIN (INR) | ACTUAL PER DAY MARGIN (USD)
Atul | Optum | CCO/0023 | PNSO - CCI | 100% | Completed | Completed | 9465600 | 8249760 | 1215840 | 87.16% | 2016-06-08 | 2016-08-20 | 120 | 86 | 638.04 | 138.7% | 2016-08-26 | 50 | 312.1 | 147.2% | 720000 | 3828240 | 10000 | 6670 | 6695600 | 5630690 | 70.74% | 59.49% | 14555.6522 | 242.5942 | 8824.9796 | 147.083
|  |  | PNSO - GLO | 95% | Go-Live | 2018-03-31 |  |  |  |  | 2016-07-15 |  | 151 | 144 |  |  | 2016-08-26 | 130 |  |  | 906000
|  |  | PNSO - Author | 100% | Completed | Completed |  |  |  |  | 2016-06-13 | 2016-08-20 | 165 | 165 |  |  | 2016-08-26 | 24 |  |  | 990000
|  |  | PNSO-MPQ | 100% | Completed | Completed |  |  |  |  | 2016-08-24 | 2016-10-25 | 24 | 24 |  |  | 2016-08-26 | 8 |  |  | 144000
|  | CCO/0024 | ID Creation | 95% | Go-Live | 2018-03-15 | 1496000 | 1196800 | 299200 | 80% | 2016-07-22 |  | 60 | 57 | 120 | 200% | 2016-08-26 | 36 | 34.26 | 95.17% | 360000 | 720000 | 5000 | 1612 | 1131000 | 774388 | 75.6% | 51.76% | 18850 | 314.1667 | 12906.4667 | 215.1078
|  | CCO/0036 | UMR | 85% | On Hold | Hold | 3372030 | 1686015 | 1686015 | 50% | 2016-12-05 |  | 131 |  | 29.5 | 22.52% |  |  |  |  | 786000 | 177000 | 20000 | 0 | 2566030 | 3195030 | 76.1% | 94.75% | 19588.0153 | 326.4669 | 24389.542 | 406.4924
|  | CCO/0039 | M&R Claims | 95% | Go-Live | 2018-03-31 | 2976735 | 2083715 | 893020 | 70% | 2017-01-16 |  | 86 |  |  | 0% |  |  |  |  | 516000 | 0 | 0 | 7196 | 2460735 | 2969539 | 82.67% | 99.76%
|  | CCO/0040 | E&I | 90% | Go-Live | 2018-03-31 | 1895055 | 1326539 | 568516 | 70% | 2017-01-16 |  | 112 |  |  | 0% |  |  |  |  | 672000 | 0 | 0 | 0 | 1223055 | 1895055 | 64.54% | 100%
|  | CCO/0038 | M&R UBH | 75% | On Hold | Hold | 3880556 | 1164167 | 2716389 | 30% | 2017-01-09 |  | 140 |  |  | 0% |  |  |  |  | 840000 | 0 |  | 0 | 3040556 | 3880556 | 78.35% | 100%
|  | CCO/0051 | E&I Support | 90% | On Hold | UAT-15th Jan'18 | 6120000 | 4080000 | 2040000 | 66.67% | 2017-04-25 |  | 133 |  |  | 0% |  |  |  |  | 798000 | 0 | 15000 | 0 | 5307000 | 6120000 | 86.72% | 100%
|  | CCO/0048 | SMS Missing | 70% | On Hold | Hold | 4447200 | 3113040 | 1334160 | 70% | 2017-04-24 |  | 196 |  |  | 0% |  |  |  |  | 1176000 | 0 | 67800 | 20785 | 3203400 | 4426415 | 72.03% | 99.53% | 28613.1977 | 476.8866 | 34529.5233 | 575.4921
|  | CCO/0059 | Billing | 95% | Go-Live | 2018-03-15 | 1836000 | 1285200 | 550800 | 70% | 2017-08-14 |  | 81 |  | 190 | 234.6% |  |  |  |  | 486000 | 1140000 | 5000 | 0 | 1345000 | 696000 | 73.26% | 37.91%
|  | CCO/0060 | Chiro | 100% | Completed | 2018-02-28 | 1020000 | 1020000 | 0 | 100% | 2017-09-21 |  | 50 |  | 80 | 160% |  |  |  |  | 300000 | 480000 | 5000 | 0 | 715000 | 540000 | 70.1% | 52.94%
|  | CCO/0061 | TOPs | 30% | On Hold | Hold | 3570000 | 1071000 | 2499000 | 30% | 2017-09-27 |  | 159 |  |  | 0% |  |  |  |  | 954000 | 0 | 5000 | 0 | 2611000 | 3570000 | 73.14% | 100%
|  | CCO/0065 | Prime Plan Change
|  |  | Total |  |  |  | 40079176 | 26276236 | 13802940
Ish | Kotak-I | CCO/0045 | Payment Gateway | 100% | Completed | 2017-11-06 | 1186800 | 1186800 | 0 | 100% | 2017-02-14 | 2017-11-06 | 52 |  |  | 0% |  |  |  |  | 312000 | 0 | 63966 | 73813 | 810834 | 1112987 | 68.32% | 93.78%
| Kotak-I | CCO/0046 | Salary Processing | 100% | Completed | 2017-12-15 | 968760 | 968760 | 0 | 100% | 2017-02-13 | 2017-12-15 | 51 |  |  | 0% |  |  |  |  | 306000 | 0 | 145300 | 256121 | 517460 | 712639 | 53.41% | 73.56%
| Kotak-I | CCO/0044 | EEFC | 90% | Cancelled | 2018-01-19 | 1104000 | 772800 | 331200 | 70% | 2017-02-21 |  | 46 |  |  | 0% |  |  |  |  | 276000 | 0 | 184420 | 204020 | 643580 | 899980 | 58.3% | 81.52%
| Kotak-I | CCO/0043 | Nostro | 90% | Cancelled | 2018-01-19 | 812475 | 568733 | 243742 | 70% | 2017-02-21 |  | 28 |  |  | 0% |  |  |  |  | 168000 | 0 | 5000 | 5000 | 639475 | 807475 | 78.71% | 99.38%
[7 empty] | 4072035 | 3497093 | 574942
| Kotak-II |  | IMPS and UPI Comp. | 60% | Dev | 2018-03-07 | 780000 | 312000 | 468000 | 40% | 2017-09-11 | 2018-01-12 | 124 | 134 |  | 0% |  |  |  |  | 744000 | 0 | 117667 | 39642.3333 | -81667 | 740357.6667 | -10.47% | 94.92%
| Kotak-II |  | ATM Complaints | 50% | Dev | 2018-03-12 | 1040000 | 416000 | 624000 | 40% | 2017-09-12 | 2018-01-17 | 130 | 145 |  | 0% |  |  |  |  | 780000 | 0 | 117667 | 39642.3333 | 142333 | 1000357.6667 | 13.69% | 96.19%
| Kotak-II |  | ATM Recon | 40% | Dev | 2018-03-23 |  |  | 0 |  | 2017-09-11 |  | 110 | 117 |  | 0% |  |  |  |  | 660000 | 0 | 117667 | 39642.3333 | -777667 | -39642.3333 | #DIV/0! | #DIV/0!
| Kotak-II |  | POS Complaints | 40% | Dev | 2018-03-16 | [6 empty] | 110 | 117 |  | 0% |  |  |  |  | 660000 |  | 303000 | 39642.3333 | -963000 | -39642.3333 | #DIV/0! | #DIV/0!
| Kotak-II |  | CRN Insta Kits | 15% | On Hold | 2017-10-13 | [14 empty] | 0 | 0 | [5 empty] | #DIV/0!
|  |  | Total |  |  |  | 1820000 | 728000 | 1092000
Ish | Oman Arab Bank | CCO/0062 | ATM Reconciliation | 90% | Go-Live | 2018-02-26 | 4560000 | 1824000 | 2736000 | 40% | 2017-11-15 | 2017-12-17 | 49 | 59 | 30 | 61.22% |  |  |  |  | 294000 | 180000 | 1291560 | 645286 | 2416440 | 3374714 | 52.99% | 25.99%
| Oman Arab Bank |  | Outgoing Chargeback | 90% | Go-Live | 2018-02-26 |  |  |  |  | 2017-11-19 | 2017-12-25 | 49 | 59 | 30 | 61.22% |  |  |  |  | 294000 | 180000
| Oman Arab Bank |  | Incoming Chargeback | 80% | Go-Live | 2018-02-26 |  |  |  |  | 2017-11-21 | 2017-01-28 | 44 | 44 | 30 | 68.18% |  |  |  |  | 264000 | 180000
|  |  | Total |  |  |  | 4560000 | 1824000 | 2736000
Saransh | FADV | CCO/0058 | DQF Express |  |  |  | 22200000 | 14400000 | 7800000 | 64.86% | 2017-08-24 |  | 270 |  |  | 0% |  |  |  |  | 1620000 | 0 | 589000 | 928931 | 19991000 | 21271069 | 90.05% | 95.82%
Saransh | FADV |  | CSPi |  | BRD
|  |  | Total |  |  |  | 22200000 | 14400000 | 7800000
Ish | ICICI | CCO/0049 | ICICI Support |  |  |  | 2400000 | 1700000 | 700000 | 70.83% | 15-Arp-17 | 2017-04-15 | 317 |  |  | 0% | - | 0 | 0 | #DIV/0! | 1902000 | 0 | 75600 | 0 | 422400 | 2400000 | 17.6% | 100% | 1332.4921 | 22.2082 | 7570.9779 | 126.183
Janhvi | Max Life | CCO/0063 | Max life |  |  |  | 800000 | 364000 | 436000 | 45.5% | 2017-12-14 | 2018-01-30 | 62 | [7 empty] | 372000 | 0 | 5000 |  | 423000 | 800000 | 52.88% | 100%
Dinesh | Bank Dhofar | CCO/0064 | Bank Dhofar |  |  |  | 2658000 | 696000 | 1962000 | 26.19% | 2017-11-30 | 2018-03-10 | 100 |  |  | 0% |  |  |  |  | 600000
Dinesh | Scope | CCO/0050 | Standard Chartered |  |  |  | 54000000 | 36000000 | 18000000 | 100% | 2017-05-01 |  | 2440 |  |  | 0% | - | 0 | 0 | 0% | 14640000 | 0 | 2193800 | 1792567 | 37166200 | 52207433 | 68.83% | 96.68% | 15232.0492 | 253.8675 | 21396.4889 | 356.6081
Atul | UHG RA |  | UHG |  |  |  | 1716000 | 858000 | 858000
Amit | Genpact |  | Genpact |  |  |  | 2217600
|  |  | Total |  |  |  | 63791600 | 39618000 | 21956000
POC's
OWNER | CLIENT | PROJECT CODE | PROCESS NAME | PROJECT COMPLETION % | CURRENT PHASE | CURRENT PHASE COMPLETION DATE (EXPECTED) | PO VALUE | BILLING DONE TILL DATE | BILLING PENDING | REVENUE ACHIEVED (%) | START DATE (ACTUAL) | PROJECT END DATE | BUDGETED EFFORT (MAN DAYS) with CR | BUDGETED EFFORT (MAN DAYS) without CR | ACTUAL EFFORT BURNT (MAN DAYS)-OVERALL | % RESOURCE UTILIZATION | REVISED START DATE (PLANNED) | REVISED EFFORT + CR (MAN DAYS) | ACTUAL EFFORT BURNT (MAN DAYS) | % RESOURCE UTILIZATION | BUDGETED SALARY EXPENSE (ACTUAL PLANNED EFFORT*PER MAN DAY RATE) | ACTUAL SALARY COST (ACTUAL EFFORT*PER MAN DAY RATE) | BUDGETED OVERHEAD COST | ACTUAL OVERHEAD COST | PROJECT OVERALL MARGIN (PLANNED) | PROJECT OVERALL MARGIN (ACTUAL) | PROJECT OVERALL MARGIN (PLANNED) % | PROJECT OVERALL MARGIN (ACTUAL) % | PLANNED PER DAY MARGIN (INR) | PLANNED PER DAY MARGIN (USD) | ACTUAL PER DAY MARGIN (INR) | ACTUAL PER DAY MARGIN (USD)
Janhvi | Benline |  | Bill of Lading |  | UAT + Dashboard development | 2017-12-20 | 3420000 | 1710000 | 1710000 | 50% | 2017-12-12 | 2018-01-09 | 18 |  | 20 | 111.1% |  |  |  |  | 108000 | 120000 | 0 | 0 | 3312000 | 3300000 | 96.84% | 96.49%
Saransh | Courts | CCO/POC/0018 | POC | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Saransh | AmBank |  | 3 Process - Pilot
Saransh | Panasonic | CCO/POC/0017 | ELD |  | Demo Shared | [5 empty] | 2017-12-22 | 2017-12-27 | 5 |  |  | 0% |  |  |  |  | 30000 | 0 | 0 | 0 | -30000 | 0 | #DIV/0! | #DIV/0!
Saransh | Panasonic |  | Factory reconciliation |  | Login and system access to be assessed | [5 empty] | 2017-12-27 | Mid Jan | [10 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Saransh | OneIndia |  | MT9 40 Upload | [7 empty] | 2017-12-12 | 2017-12-18 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Saransh | OneIndia |  | VB Script | [7 empty] | 2018-02-08 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Saransh | BDO |  | PTDC, FINCON | [7 empty] | 2018-01-29 | 2018-02-07 | [8 empty] | 0 | 0
Saransh | Cebuana Lhuiller |  | Remittance Authorization | [7 empty] | 2018-01-28 | 2018-02-20
Saransh | Merck |  | PR to PO | [7 empty] | 2018-02-05 | 2018-02-09
Saransh | Daimler |  | Process on Pay | [7 empty] | 2018-02-05 | 2018-02-12
Saransh | Globe Telecom |  | ISG, CXM
Saransh | MayBank | [9 empty] | 2018-01-30 | 2018-01-31
Vishal | Emirates Airlines | CCO/POC/0019 | POC | [7 empty] | 2017-12-17 | 2017-12-29 | 10 |  |  | 0% |  |  |  |  | 60000 | 0
Vishal | National Bank of Oman |  | POC | [7 empty] | 2017-11-30 | 2018-01-08 | 15 | [7 empty] | 90000 | 0

## Sheet2 (hidden)
AM | Client | Process | Completion % | Current Phase | Current Phase Completion Date | Start Date | End Date | Status | Challenges
Atul | Optum | PNSO - CCI | 100% | Completed | Completed | 2016-06-08 | 2016-08-20
0 |  | PNSO - GLO | 95% | Go-Live | 2018-03-31 | 2016-07-15 | 0 | UAT sign off agreed by 30-Jan-18
0 |  | PNSO - Author | 100% | Completed | Completed | 2016-06-13 | 2016-08-20
0 |  | PNSO-MPQ | 100% | Completed | Completed | 2016-08-24 | 2016-10-25
0 |  | ID Creation | 95% | Go-Live | 2018-03-15 | 2016-07-22 | 0 | Go Live sign off expected by 15-Feb-18
0 |  | UMR | 85% | On Hold | Hold | 2016-12-05 | 0 | EDSS application issue
0 |  | M&R Claims | 95% | Go-Live | 2018-03-31 | 2017-01-16 | 0 | UAT sign off agreed by 15-Jan-18
0 |  | E&I | 90% | Go-Live | 2018-03-31 | 2017-01-16 | 0 | UAT sign off agreed by 15-Jan-18
0 |  | M&R UBH | 75% | On Hold | Hold | 2017-01-09 | 0 | EDSS application issue
0 |  | E&I Support | 90% | On Hold | UAT-15th Jan'18 | 2017-04-25 | 0
0 |  | SMS Missing | 70% | On Hold | Hold | 2017-04-24 | 0 | UAT sign off expected by 15-Dec-17
0 |  | Billing | 95% | Go-Live | 2018-03-15 | 2017-08-14 | 0 | UAT sign off agreed by 15-Dec-17
0 |  | Chiro | 100% | Completed | 2018-02-28 | 2017-09-21 | 0 | UAT sign off expected by 15-Dec-17
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Adopted Agile methodology for the TOPS project (first onshore paid project). The success of this project will get us a lot of new projects from this line of business in 2018
Ish | Kotak-I | Payment Gateway | 100% | Completed | 2017-11-06 | 2017-02-14 | 2017-11-06 | Combined solution (Nostro & EEFC) will be deployed this week in Prod and will be signed off by next week. | Users are reluctant in using the solution which can delay the Prod sign off.
0 |  | Salary Processing | 100% | Completed | 2017-12-15 | 2017-02-13 | 2017-12-15
0 |  | EEFC | 90% | Cancelled | 2018-01-19 | 2017-02-21 | 0
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | No functional issues reported since 17th Nov. Working on Performance and multiple Robo implementations. | The client sql server response time & non- standard input files creating issues in successful execution of solution. Implementation of multiple Robo can delay the sign off.
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | Requirements changed after signing off the BRD. Only partial development can be done because of the limited data to work
0 |  | IMPS and UPI Comp. | 60% | Dev | 2018-03-07 | 2017-09-11 | 2018-01-12
0 |  | ATM Complaints | 50% | Dev | 2018-03-12 | 2017-09-12 | 2018-01-17
0 |  | POS Complaints | 40% | Dev | 2018-03-16 | 0 | 0
0 |  | CRN Insta Kits | 15% | On Hold | 2017-10-13 | 0 | 0
Ish | Oman Arab Bank | ATM Reconciliation | 90% | Go-Live | 2018-02-26 | 2017-11-15 | 2017-12-17 | Development completed and integration testing is ON. Solution was demonstrated to client last week | BRD Sign off – BRD sign off is pending for all 3 processes. Will be done after discussion with the Info security team of OAB next week Change in scope – There are some additional requirement which were not part of initial scope as per process map shared. Also, a part of the process (CCMS for incoming chargeback) doesn’t exist as on today which could create challenge in development and testing.
0 |  | Outgoing Chargeback | 90% | Go-Live | 2018-02-26 | 2017-11-19 | 2017-12-25 | Development started this week and targeting to complete by 13th Dec.
0 |  | Incoming Chargeback | 80% | Go-Live | 2018-02-26 | 2017-11-21 | 2017-01-28 | Development will start from 13th Dec and will be completed by 7th Jan 18.
Dinesh | Scope | Standard Chartered | 0% | 0% | 0 | 2017-05-01 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Post sign off in August 17, Post paid agents were also allowed to use the solution. Initially, usage was good (120+ agents) but subsequently TU solution is not being used. | New set of agents not familiar with TU features. Untrained agents from outsourced vendor. Lack of supervision, push by Celcom management
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | Dependency on Celcom for LDAP integration, MBSS and CISO testing. Expected to get closed in Nov-Dec when Celcom finally phases out Kenan application
Saransh | FADV | DQF Express | 0% | 0% | 0 | 2017-08-24 | 0
Janhvi | Benline | Bill of Lading | 0% | UAT + Dashboard development | 2017-12-20 | 2017-12-12 | 2018-01-09
Ish | ICICI | ICICI Support | 0% | 0% | 0 | 15-Arp-17 | 2017-04-15
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | All 3 sites rolled out. Project expected to close in Dec 17
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | UAT sign off received. Go-Live is pending. Expected to close in Dec 17
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Only 17 man days support is left for billing. Will get completed in Dec 17.
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Project will get completed by 20th Dec 17.
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Saransh | OneIndia | MT9 40 Upload | 0% | 0% | 0 | 2017-12-12 | 2017-12-18
Saransh | Courts | POC | 0% | 0% | 0 | 0 | 0
Saransh | Panasonic | ELD | 0% | Demo Shared | 0 | 2017-12-22 | 2017-12-27
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Consolidated Sheet (hidden)
Working days-Training, leave | Resources | No. of Productivity | Averange billing | Department Expenses |  |  | Cost Per employee
[7 empty] | Deepak | 6000
[7 empty] | RPA | 5000
HEAD | RPA PROJECTS
| OPTUM GLOBAL SOLUTION | [6 empty] | ICICI PO I | [5 empty] | ICICI PO II |  |  | ICICI PO III | SCOPE |  |  | Metro Bank | GIC Mgmt Console | Cross Sell/Up Sell | Celcom Support
| CCO/0023 |  |  | CCO/0024 | CCO/0026 | CCO/0025 | CCO/0021 | CCO/0009 | [9 empty] | CCO/0018 | CCO/0020 | CCO/0022 | CCO/0028
| PNSO - CCI | PNSO - GLO | PNSO - AUTHOR/MPQ | ID CREATION | UHCG | SBC | RxCCR | ATM Dispute I | Charge Reversal | Charge Back | ECS Debit | Fund Authorization | FCRM Loan | CORP-Cust ID | Reversal of Charges | CMS Master Setup | ATM Dispute II | SCOPE TRADE | SCOPE FM | SCOPE Rel ID
PO Value | 9465600 |  |  | 1496000 | 3386400 | 2516000 | 1935630 | 7207200 | [5 empty] | 2679227 |  |  | 200000 | 2537500 | 3737500 | 1125000 | 1680000
Billing Done till date | 2839680 |  |  | 1196800 | 1693200 | 754800 | 1196800 | 1801800 | [5 empty] | 669807 |  |  | 200000 | 2537500 | 3737500 | 731250 | 840000
Revenue Achieved (%) | 30% |  |  | 80% | 50% | 30% | 61.83% | 25% | [5 empty] | 25% |  |  | 100% | 100% | 100% | 65% | 50%
Actual Project Start Date | 2016-06-08 | 2016-06-12 | 2016-06-13 | 2016-07-07 | 2016-07-14 | 2016-06-30 | 2016-03-26 | 2015-10-15 | [5 empty] | 2015-12-30 |  |  | 2016-08-22 | 2016-04-04 | 2016-04-04 | 2016-07-08 | 2016-09-26
Project Duration in weeks | 10 weeks | 10 weeks | 10 weeks / 8 weeks | 8.5 weeks | 9.2 weeks | 7 weeks | 7 weeks | 7.3 Weeks |  |  | 6.4 Weeks | 7.1 Weeks | [8 empty] | 5 Weeks
Budgeted efforts (Man-days) | 86 | 0 | 164 | 57 | 0 | 73 | 0 | 480 |  |  |  |  | 0 | 185 |  |  | 0 | 133 | 228 | 96 | 0
Actual effort (Man-days) - Overall | 497.47 |  |  | 86.82 | 68.75 | 244.69 | 102 | 313.07 | [9 empty] | 37 | 55.01 | 181.31 | 25
Revised Start Date | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | [5 empty] | 2016-08-26 |  |  | 2016-08-22 | 2016-08-26 | 2016-08-26 | 2016-08-26 | -
Revised effort (Man-days) from 26 Aug'16 | 16 | 123 | 32 | 33 | 99 | 40 | 0 | 0 |  |  |  |  | 70 | 0 |  |  | 25 | 15 | 16 | 30 | 25
Change Request | 34 | 7 | 0 | 3 | 0 | 35 | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 11
Actual effort (Man-days) till 8th Nov 2016 | 275.97 |  |  | 34.13 | 66.75 | 167 | 0 | 273.57 | [9 empty] | 20 | 30.76 | 139.56 | 25
Planned Project Completion Date | 2016-11-11 | 2016-11-18 | 2016-11-04 | On Hold | 2016-11-18 | 2016-11-04 | On Hold | 2016-06-15 | 2016-05-24 | 2016-10-03 | 2016-10-07 | 2016-11-09 | 2016-12-09 | 2016-10-07 | 2016-11-11 | 2016-12-30 | 2016-11-08 | 2016-10-03 | 2016-09-08 | 2016-11-11 | 2016-10-28
Project Percentage Completed
Resource Utilization Variance
Budgeted Overheads Cost | 5000 | 0 | 5000 | 5000 | 0 | 5000 | 10000 | 72000 | [9 empty] | 0 | 0 | 0 | 418000
Actual Overheads Cost | 0 |  |  | 0 | 0 | 0 | 104 | 663149 | [9 empty] | 260473 | 355985 | 132717 | 162870
Salary Overhead
Project Overall Margin (Planned)
Project Overall Margin (Actual)
Project Overall Margin (Planned) %
Project Overall Margin (Actual) %

## Sheet3 (hidden)
2017-12-22
Optum | COE Discussion
To discuss with nidhi for UMR and M&R UBH
Support Contract - to finalize effort days
Playbook done-Shared with Atul Agarwal. He is creating his own team on OpenSpan and Uipath.
1 Trainer is joing in 2nd week of Jan
OAB | 31st Dec is closure but nothing developed
ATM Recon gone for LIVE
UAT Started for Outgoing Chargeback
No update on Incoming Chargeback
Kotak-1 | Salary Processing: On 26th Dec we need to put it on UAT for testing of Multi Robo functionality. It will continue till Mid Feb because of new enhancement. Volume is 1000/2000/3000. 1 Robo can do 50 SR in a day,3-4 SR will do 1 Go. To process 150 SR in Jan end, parallely we are working on performance so that SR can increase. Aqib cannot release 2 New CR's have come up. Production issue depenceny on Aqib. He is working on Multi Robo functionality so he hasn't look on Production issue.
EEFC, Nostro is on top prioirty.
Kotak-2 | Started in 1st week of Jan
UPI development should complete by next week, hard code development is pending. To track closely code review etc.
ATM Complaints-2nd week of Jan and last week in production
ATM Recon-Sign off expected on Friday, 2 developer identified
POS & CRN-Need 1 developer(Arjun). 1 .net resource required for dashboard
Oman Arab Bank | Dinesh to speak with Ish
Scanning Tool OCR | TCL using abby or flexy capture
To develop 4 template. Is there any other alternate to save cost and time
we have 4 Cases-HDFC Ergo, Bajaj Aliance, TCL and
To discuss with Saransh directly
ICICI Support | To check with Ish
POC | BDO Bank remotely finshed 1-2 process. To speak with Pradeep Sir. Happypath
If issue then will change
POC status-?
Exception POC to be finish by 7th Jan
FADV | 3 Priority-
Fixing the issue
unattended execution
Plan in order to close DQF

## Project percentage
OMAN ARAB BANK
ACTIVITY PHASE % COMPLETED | OVERALL % COMPLETED | % ACTIVITY WEIGHTAGE | TASK NAME | DURATION | PLANNED START | PLANNED FINISH | ACTUAL START | ESTIMATED FINISH | ACTUAL FINISH | RESOURCE NAME
ATM RECON
| 26.5% | 100% |  |  | 2016-05-26 | 2016-06-12
100% | 15% | 15% | Process Study |  | 2016-05-26
80% | 4% | 5% | BRD
50% | 7.5% | 15% | Design
0% | 0% | 45% | Development | 14 | 2016-09-01 | 2016-09-20
0% | 0% | 10% | UAT | 5 | 2016-09-21 | 2016-09-27
0% | 0% | 5% | UAT Signoff | 1 | 2016-09-28 | 2016-09-28
0% | 0% | 5% | GO Live | 2 | 2016-09-29 | 2016-09-30
OUTGOING CHARGEBACK
ACTIVITY PHASE % COMPLETED | OVERALL % COMPLETED | % ACTIVITY WEIGHTAGE | TASK NAME | DURATION | PLANNED START | PLANNED FINISH | ACTUAL START | ESTIMATED FINISH | ACTUAL FINISH | RESOURCE NAME
| 90% | 100% |  |  | 2016-05-26 | 2016-06-12
100% | 15% | 15% | Process Study |  | 2016-05-26
100% | 5% | 5% | BRD
100% | 15% | 15% | Design
100% | 45% | 45% | Development | 14 | 2016-09-01 | 2016-09-20
100% | 10% | 10% | UAT | 5 | 2016-09-21 | 2016-09-27
0% | 0% | 5% | UAT Signoff | 1 | 2016-09-28 | 2016-09-28
0% | 0% | 5% | GO Live | 2 | 2016-09-29 | 2016-09-30
INCOMING CHARGEBACK
ACTIVITY PHASE % COMPLETED | OVERALL % COMPLETED | % ACTIVITY WEIGHTAGE | TASK NAME | DURATION | PLANNED START | PLANNED FINISH | ACTUAL START | ESTIMATED FINISH | ACTUAL FINISH | RESOURCE NAME
| 80% | 100% |  |  | 2016-05-26 | 2016-06-12
100% | 15% | 15% | Process Study |  | 2016-05-26
100% | 5% | 5% | BRD
100% | 15% | 15% | Design
100% | 45% | 45% | Development | 14 | 2016-09-01 | 2016-09-20
0% | 0% | 10% | UAT | 5 | 2016-09-21 | 2016-09-27
0% | 0% | 5% | UAT Signoff | 1 | 2016-09-28 | 2016-09-28
0% | 0% | 5% | GO Live | 2 | 2016-09-29 | 2016-09-30

## Weekly Status Report
WEEKLY STATUS REPORT CLIENT - OMAN ARAB BANK
DATE OF REPORTING |  | 2017-12-06 |  | REPORTING PERIOD |  |  | 29-Nov-17 TO 5-Dec-17
PROCESS NAME |  | CURRENT PHASE | CURRENT PHASE COMPLETION DATE | OVERALL PROJECT COMPLETED (%) | PROJECT COMPLETION DATE (PLANNED) |  | PROJECT COMPLETION DATE (EXPECTED) | SCHEDULE VARIANCE | CHALLENGES
ATM POS RECONCILIATION |  | Development | 2017-12-03 | 70% | 2017-12-17 |  | 2017-12-17 | 0 | BRD sign off pending
OUTGOING CHARGEBACK |  | Development | 2017-12-13 | 30% | 2017-12-25 |  | 2017-12-25 | 0 | BRD sign off pending
INCOMING CHARGEBACK |  | BRD sign off | 2017-12-03 | 15% | 2017-01-30 |  | 2017-01-30 | 0 | BRD sign off pending
TASK COMPLETED LAST WEEK | [5 empty] | TASK PLANNED FOR THIS WEEK
1. Development completed for ATM Recon. 2. Demo done of ATM Recon with all the stakeholders. 3. Development started for Outgoing Chargeback. 4. Project plan completed for Incoming Chargeback. 5. BRD completed for all 3 processes. | [5 empty] | 1. Start UAT for ATM recon. 2. BRD sign off for all 3 processes. 3. Development completion for the Outgoing Chargeback. 4. Start development for Incoming Chargeback. 5. Revisit the Incoming project plan.
CRITICAL ISSUES | [5 empty] | CRITICAL RISKS
1. Unavailability of application access and test data will impact the project timelines. | [5 empty] | 1. Application slowness will create the performance issues in the solution.
PROCESS NAME | PROJECT STATUS
| PROCESS STUDY | BRD CREATION | BRD SIGNOFF | DESIGN |  | DEVELOPMENT | UAT | LIVE | PROJECT SIGN OFF
ATM RECONCILIATION | Completed | Completed | WIP | Completed |  | Completed
OUTGOING CHARGEBACK | Completed | WIP
INCOMING CHARGEBACK | Completed | WIP
Formulas:
SCHEDULE VARIANCE = NETWORKDAYS([PROJECT COMPLETION DATE (PLANNED)],[PROJECT COMPLETION DATE (EXPECTED)])

## Change Request Logs
CHANGE REQUESTS
PROCESS NAME | CHANGE | CATEGORY | INTRODUCE IN PHASE | REPORTED DATE | CHANGE DESCRIPTION | EFFORTS DAYS | CHARGABLE / NOT CHARGABLE | STATUS | COMMENTS
Salary Processing | Change in the solution to process SR on same day |  | Development | 2017-03-28 | To make the solution run on same day using single Robo | 5 | Not Charged | Completed | This was changed to proccess all the SRs on day.
| Sending exception mails to users |  | Development | 2017-04-17 | To sent mail of all the exceptions to the users. | 1 | Not Charged | Completed | These mails are to information to user about all the exceptions.
| Exception log in webpage |  | Development | 2017-04-25 | To include the Webpage approach to show all the exceptions to user. | 4 | Not Charged | Completed | Because of communication gap this was missed while developing "Sending Mails to user" change and build later.
| New requirements |  | UAT | 2017-05-02 | 1. Individual salary more than 10 Lacs. 2. Same SR to be processed on the same day if the entire file is rejected for any exception. | 1 | Not Charged | Completed | 1st is handled but 2nd required additional efforts.
| Change in the Siebel application |  | UAT | 2017-05-12 | The Siebel application UI changed when login with Shilpa's user ID | 1 | Not Charged | Completed | The Tab menu (UI) on the “UATTESTUSER2” and “SHILPAG” user's varied in Siebel, so solution was changed as well.
| Revised approach of checking the amount in finacle |  | UAT | 2017-05-08 | Robo shall keep a log of all the records that has been processed in a day. Therefore there would be one excel file (Daily Transaction Log)containing the records processed that day. | NA | NA | NA | This was ruled out as Robo still have dependency of checking Finacle (Freeze & Dormant a/c )
| Change in Siebel service list |  | UAT | 2017-05-10 | In Siebel "My service request" menu needs to be changed to “My Team’s Service Request” to download all the SRs. | 1 | Not Charged | Completed | This is to handle the change in the selection of the Siebel menu.
| Programmatic access Allow and Deny in Outlook |  | UAT | 2017-05-10 | In VDI, because of the outlook settings we are getting few pop-ups because of which Robo got stuck until unless someone manually clicks on OK | 3 | Not Charged | Completed | Recommended solution is to perform this task using email exchange server skipping outlook. Same will be implemented to Payment Gateway. This is resolved by changing setting.
| Change in Finacle application |  | UAT | 2017-05-24 | 1. Memo Pad pop-up to be handle for Account level 2. Account not valid pop-up 3. Pop-up while mailing from Outlook 4. 3 types of Freeze to be handle | 1 | Charged - Approved | Completed | This is to handle the 2 new pops in Finacle application.
| Change in requirement with availability of Account Freeze test data |  | UAT | 2017-05-26 | With the availability of account freeze data, 3 flows(Credit, Debit & Total freeze) were added against the earlier requirement of only 1 flow of Account freeze exist. | 1 | Charged - Approved | Completed | These are now handle in solution.
| Change in Finacle account checking from all to random number and making it configurable. Also, marking SR to WIP status. |  | UAT | 2017-06-30 | This change request have change in Account checking in finacle from all to random numbers. That is configurable. This also brings a new status WIP to handle already credited cases. Also it will change the sequence of Name mismatch display in Dashboard. | 6 | Charged - Approved | Completed
| To revert the solution for handling the "resolved" status of SR. |  | UAT | 2017-06-30 | As the resolved status is not possible to use in Siebel, solution is reverted to handle the "Resolved" status of SR. | 1 | Charged - Approved | Completed
| New status of HOLD_ROBO |  | UAT | 2017-07-28 | While ROBO picks the SR for processing the SR with the status as “HOLD_ROBO” shall be picked in place of “HOLD” which is being used currently. | 3 | Charged - Approved | Completed | From - Ankur Mail Subject - Salary Processing changes Date & Time - Friday, July 28, 2017 5:04 PM
Payment Gateway | Change in the Solution to include front office. |  | Development | 2017-03-21 | Including the Front office and making the solution real time to be used by them | 4 | Charged - Approved | Completed | Taking input from Agent in UI form and provide runtime information to him during call.
| Change in solution to remove the front office only. |  | Development | 2017-04-17 | Removing the front office and making it to the backend only | 3 | Charged - Approved | Completed | Removing the Agent form and pushing all the data in DB to process the SRs further.
| Change in billdesk flow from 1 to 5 after getting the data. |  | Development | 2017-04-13 | With the availability of Bill desk aggregator data, 5 flows were added against the earlier requirement of only 1 flow. | 3 | Charged - Approved | Completed | 3 out of 5 are done and rest 2 are pushed for next phase.
| New requirements |  | Development | 2017-04-13 | Remaining Billdesk Aggregator & remaining requirement as per mail (20th May). | 5 | Postponed | Postponed | Postponed for next phase w.r.t to mail dated 20th May 17
| Required 4 parameter moved from Summary field to newly created fields |  | Prod | 2017-08-16 | As discussed, the following fields are available in the SIEBEL UAT • Dispute Date • Dispute Amount • Narration • Account Number | 3 | Charged - Approved |  | Mail From: Ankur Bhargava Date/time: Wednesday, August 16, 2017 2:41 PM Subject: FW: RPA - Approval for new field in SIEBEL Approved by Haresh - 17 Aug 17
EEFC Lien Marking | New changes before Go Live |  | Go live | 2017-05-02 | 1. The ROBO shall get invoked for Lien Marking once the Deal Id is populated on the OMP Platform 2. The ROBO shall populate “CPC” in the filed “lien reason” and “RET Deal ID” should be populated in “Lien remark” field | 2 | Charged - Approved | Completed | Development delay because of the issue with OMP raised on 4th May and later RET ID was unavailable till today.
| 1. OMP Table Change |  | Go live | 2017-05-17 | For the TOM tab, there is an additional column “Original OMP Id”. | 1 | Charged - Approved | Completed | This is change in application because of which solution need to be changed.
| New changes in UAT |  | UAT II | 2017-06-08 | 1. ROBO shall wait for 30 sec after the Finacle form has been filled to get the RET Id. 2. While user selects “EEFC / Nostro” in the “Underlying Column”, the ROBO shall validate that all the mandatory fields | 1 | Not Charged - Approved | Completed
Nostro | New changes before Go Live |  | Go live | 2017-05-04 | Modification in the NOSTRO BALANCE check process | 7 | Charged - Approved | Completed | This is new requirement to calculate the balance in account.
| 1. OMP Table Change |  | Go live | 2017-05-17 | For the TOM tab, there is an additional column “Original OMP Id”. | 1 | Charged - Approved | Completed | This is change in application because of which solution need to be changed.
| New changes in UAT |  | UAT II | 2017-06-08 | While user selects “EEFC / Nostro” in the “Underlying Column”, the ROBO shall validate that all the mandatory fields | 1 | Not Charged - Approved | Completed
NOT CHARGED |  |  |  | CHARGED & APPROVED |  |  | RULED OUT AT PRESENT
High Must Have |  |  |  | Medium - Should have |  |  | Low - Good to have

## Projection List
Services - Order In Hands | [10 empty] | 2017-02-02 | 2017-02-09 | 2017-02-16 | 2017-02-23 | 2017-02-28 |  | 2017-03-02 | 2017-03-09 | 2017-03-16 | 2017-03-23 | 2017-03-30
AM | Region | Client | Project | Milestone | Total PO Value | Billing Done | Pending | Hold | Next Quarter | Feb | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Mar | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | REMARKS
Atul | India | Optum-PNSO (UAT) | UHG-PNSO | f. 40% - final sign-off-40% GLO | 9465600 | 8249760 | 1215840 |  |  | 0 | [5 empty] | 1215840 |  |  |  | 1215840
Atul | India | Optum-ID Creation (UAT) | UHG-ID Creation | d. 20% on final sign-off | 1496000 | 1196800 | 299200 |  |  | 299200 |  |  |  | 299200 |  | 0 | [5 empty] | Sign off expected by 15th Feb 2018
Atul | India | Optum-UMR (On Hold) | UHG-UMR | c. 20% on UAT sign off of Duplicate & 906 (subject maximum 5 days of UAT offer) | 3372030 | 1686015 | 674406 | 674406 |  | 0 | [5 empty] | 0 | [5 empty] | on Hold, if Dev is completed for any other queue outside of PDS/SAW, we will ask for the Dev effort
Atul | India |  | UHG-UMR | d. 20% on UAT sign off of DME (subject maximum 5 days of UAT offer) |  |  | 674406 | 674406 |  | 0 | [5 empty] | 0
Atul | India |  | UHG-UMR | e. 10% on GLive sign off |  |  | 337203 | 337203 |  | 0 | [5 empty] | 0
Atul | India | Optum-M&R Claims (UAT) | UHG-M&R | c. 30% on Go Live Sign Off | 2976735 | 2083715 | 893020 |  |  | 893020 |  |  |  |  | 893020 | 0 | [5 empty] | 2 weeks post the UAT sign-off
Atul | India | UHG-E&I | UHG-E&I | c. 30% on Go Live Sign Off | 1895055 | 1326539 | 568516 |  |  | 568516 | [5 empty] | 0 | [5 empty] | 2 weeks post thee UAT sign-off
Atul | India | Optum-UBH M&R ( on Hold) | UHG-UBH | b. 40% on UAT Sign Off | 3880556 | 1164167 | 1552222.4 | 1552222.4 |  | 0 | [5 empty] | 0 | [5 empty] | Run the test cases again for a few days and provide the UAT sign-off if it runs clean. Will inform Janki to push to get the sign-off
Atul | India |  | UHG-UBH | c. 30% Go Live |  |  | 1164166.8 | 1164166.8 |  | 0 | [5 empty] | 0
Atul | India | Optum-Billing (UAT) | UHG-Billing | c. 30% Go live sign off | 1836000 | 550800 | 1285200 |  |  | 1285200 | 1285200 |  |  |  |  | 0 | [5 empty] | Expected by 31st Jan
Atul | India | Optum-SMS Missing (On Hold) | UHG-SMS Missing | c. 30% Go Live sign | 4447200 | 3113040 | 1334160 | 1334160 |  | 0 | [5 empty] | 0
Atul | India | Optum-TOPs (Development) | UHG-TOPs | b. 40% on UAT sign off | 3570000 | 1071000 | 1428000 |  | 1428000 | 0 | [5 empty] | 0 | [5 empty] | Sign off planned in End Feb 2018 Client have agreed to complete / manage the pending issues, Code review, update with change is existing requirement, testing etc. and Bring 100% accuracy (70-80%. Target to complete both PI 1 & 2 with clean UAT by 14th July. All the help, change in shift, technical help etc. is being taken care of and our PM has started providing a daily update till the closure on this project. *Post 14th July, we can expect the UAT sign-off then Go Live
Atul | India |  | UHG-TOPs | c. 30% on final sign off |  |  | 1071000 |  | 1071000 | 0 | [5 empty] | 0
Atul | India | RA | RA- BA (2) | 2 BA for 66 days | 1716000 | 858000 | 858000 |  | 858000 | [6 empty] | 0 | [5 empty] | Expected by 31st Jan
Ish | India | ICICI | ICICI- support contract | Enhancement in Robotic process automation system (RPAS) (The period of engagement is for one year from April 1, 2017 to March 31, 2018) | 2400000 | 1900000 | 500000 |  | 100000 | 0 | [5 empty] | 400000 | 200000 |  |  |  | 200000 | PO Received. Support start date April 1st. Monthly Payments, end of month. 15 day billing in April due to delay in the readiness
| India | EY | IFB | e. 5% on 1st roll out | 3650000 | 2737500 | 182500 | 182500 |  | 182500 |  |  |  | 182500 | [7 empty] | Escalated to EY, pending update / dates on milestone closure, following up with Nitin Nagpal(Project Manager)
| India |  | IFB | f. 5% on 2nd roll out |  |  | 182500 | 182500 |  | 182500 |  |  |  | 182500
| India |  | IFB | g. 10% on 3rd roll out |  |  | 365000 | 365000 |  | 365000 |  |  |  | 365000
| India |  | IFB | h. 5% on completion of one month of post go live support |  |  | 182500 | 182500 |  | 182500 |  |  |  | 182500
| India | NIIT | MSTD | d. 15% on go live sign off(without DR) | 1916325 | 1578150 | 338175 | 338175 |  | 338175 |  |  |  | 338175
Ish | India | Kotak-EEFC | EEFC Lien Marking | 30% on Project Go-Live | 1104000 | 772800 | 331200 |  |  | 0 | [5 empty] | 0
Ish | India | Kotak-Nostro | Nostro Lien Marking | 30% on Project Go-Live | 812475 | 568733 | 243742.5 |  |  | 0 | [5 empty] | 0
Amit | India | Scope | RA |  | 54000000 | 44100000 | 9900000 |  | 5400000 | 0 | [5 empty] | 4500000 | 4500000
Ish | India | Kotak-IMPS | UP_IMPS | 30% on UAT Sign off | 780000 | 312000 | 234000 |  |  | 0 | [5 empty] | 234000 |  |  | 234000
Ish | India |  | UP_IMPS | 30% on Project Go-Live |  |  | 234000 |  | 234000 | 0 | [5 empty] | 234000 | 234000
Ish | India | Kotak-ATM Dispute | ATM Dispute | 30% on UAT Sign off | 1040000 | 416000 | 312000 |  |  | 0 | [5 empty] | 312000 |  |  |  | 312000
Ish | India |  | ATM Dispute | 30% on Project Go-Live |  |  | 312000 |  | 312000 | 0 | [5 empty] | 312000 | 312000
Jahnvi | India | Max Life | RA | Technical consultants for 62 man days starting from the date of deployment, posted at MLI Gurgaon HO-On actual at the end of every month | 806000 | 715000 | 91000 |  |  | 91000 |  |  | 91000 |  |  | 0
Amit | India | Genpact | RA | Sol Architect for 6 months | 2217600 | 0 | 2217600 |  | 1478400 | 369600 |  |  |  |  | 369600 | 369600 |  |  |  |  | 369600
Ish | MENA | Oman Arab Bank | Oman Arab Bank | b. 20% on Requirement Gathering Sign off | 4560000 | 1824000 | 912000 |  |  | 912000 |  |  | 912000 |  |  | 0
Ish | MENA |  | Oman Arab Bank | c. 30% on UAT Sign off |  |  | 1368000 |  |  | 1368000 |  |  |  | 1368000 |  | 0
Ish | MENA |  | Oman Arab Bank | d. 10% on Production Deployment and Go-Live |  |  | 456000 |  |  | 456000 |  |  |  | 456000 |  | 0
Amit | MENA | Bank Dhofar | Bank Dhofar | Technical consultants for 3 months | 2088000 | 696000 | 1392000 |  |  | 696000 |  |  |  | 696000 |  | 696000 |  |  |  | 696000
Amit | MENA |  | Bank Dhofar | Training Cost | 570000 | 0 | 570000 |  | 570000
Sunil | SE & NA | AmBank | Ambank | Professional services for 125 man days | 2490000 | 0 | 2490000 |  | 2490000
|  |  | Total in INR |  | 113089576 | 76920019 | 36169557.7 | 6987239.2 | 13941400 | 8189211 | 1285200 | 0 | 1003000 | 4069875 | 1262620 | 8273440 | 5246000 | 0 | 234000 | 2223840 | 569600
[7 empty] | 274377.5167 |  |  | 136486.85 | [5 empty] | 137890.6667
16462651
52632208.7
[10 empty] | 0 | [5 empty] | 0 | [5 empty] | Move to April
[10 empty] | 0 | [5 empty] | 0 | [5 empty] | Move to May
[10 empty] | 0 | [5 empty] | 0 | [5 empty] | Move to May
[7 empty] | Total |  |  | Dec | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Dec | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | REMARKS
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 1068000 | 1068000 |  |  |  |  | 1068000 | 1068000
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 4500000 |  |  | 0 | [5 empty] | 0
[7 empty] | 1000000 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 5500000 |  |  | 1068000 | 1068000 | 0 | 0 | 0 | 0 | 1068000 | 1068000 | 0 | 0 | 0 | 0
[7 empty] | 91666.6667 |  |  | 17800 | 17800 | 0 | 0 | 0 | 0 | 17800 | 17800 | 0 | 0 | 0 | 0
[7 empty] | 41669557.7 |  |  | 9257211 | 2353200 | 0 | 1003000 | 4069875 | 1262620 | 9341440 | 6314000 | 0 | 234000 | 2223840 | 569600
[11 empty] | 2017-12-01 | 2017-12-08 | 2017-12-15 | 2017-12-22 | 2017-12-29 |  | 2017-12-01 | 2017-12-08 | 2017-12-15 | 2017-12-22 | 2017-12-29
[7 empty] | Total |  |  | Dec | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Dec | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | REMARKS
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[10 empty] | 0 | [5 empty] | 0
[10 empty] | 0 | [5 empty] | 0
[10 empty] | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | [5 empty] | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on I6: On Hold

## Defect Logs
Defination of Serverity
S1 | Defect is showstopper and need to resolved on urgent basis
S2 | Defect is not a showstopper and alternate is available
S3 | Not critical impact on functionality
<Process Name...>
S.No | Phase | Description | Category | Reported Date | Status | Closure Date | Comments
1 | Development | Robo failed to read the file | S2 | 2018-02-26 | Open |  | WIP
2 | UAT | Robo failed to login Finacle application | S1 | 2018-02-22 | WIP |  | This ready for testing
Note on B6: Functional Testing UAT Testing